## IS Issues
Application Name | Severity | Issues Description | Status of Issue | DBG Remarks
UBCS APIs - CMS Branch Collection Portal | Medium | Insecure Connection Over HTTP | Fixed
E-Stamping Sindh API | High | API Credentials in plain text in Database | Fixation in Progress
E-Stamping Sindh API | High | Insecure Connection Over HTTP | Fixation in Progress
E-Stamping Sindh API | High | Password Brute-Forced | Fixation in Progress
E-Stamping Sindh API | Medium | Challan Number information Leaking in URL | Fixation in Progress
E-Stamping Sindh API | Medium | Lack of Cookie Header Validation | Fixation in Progress
E-Stamping Sindh API | Medium | Access Token Expiry Vulnerability | Fixation in Progress
E-Stamping Sindh API | Low | Server Version Disclose | Fixation in Progress
E-Stamping Sindh API | Low | Extra Parameter Addition Vulnerability | Fixation in Progress
IBFT API for CMS Payment Portal | High | Weak Encryption Algorithm used for Authentication Credentials in API | Fixation in Progress
IBFT API for CMS Payment Portal | High | Password Brute-Forced on Authentication | Fixation in Progress
Statement of Account API of eStatement application | Low | Sensitive Data in API Logs | Fixation in Progress
CMS - Collection Portal (Bulk Account Upload – SIDA) | Low | Excel File not Encrypted | Fixation in Progress
CMS Payment Portal | High | Arbitrary File Upload | Fixed
CMS Payment Portal | High | Brute Force upon Login | Fixed
CMS Payment Portal | Medium | Autocomplete Enabled | Fixation in Progress
CMS Payment Portal | Medium | Concurrent Session Allowed | Fixed
CMS Payment Portal | Medium | Misconfigured CSP | Fixation in Progress
CMS Payment Portal | Medium | Misconfigured Cache Control | Fixed
CMS Payment Portal | Medium | Session Cookie without Secure Flag | Fixed
CMS Payment Portal | Medium | Misconfigured X-XSS Protection Header | Fixation in Progress
CMS Payment Portal | Medium | Weak OTP Complexity | Fixed
CMS Payment Portal | Medium | No Rate Limit on Resend OTP | Fixation in Progress
CMS Payment Portal | Medium | Wildcard Certificate | Fixation in Progress
PSW API | High | No Rate Limit Upon Authentciation | Fixation in Progress
PSW API | High | Insecure Transmission of Credentials | Fixation in Progress
PSW API | Medium | Improper Input Validation | Fixation in Progress
PSW API | Medium | No Length Validation | Fixation in Progress
PSW API | Medium | Server Type Disclosure | Fixation in Progress
PSW API | Low | Missing Content-Security-Policy (CSP) Header | Fixation in Progress
PSW API | Low | Missing HTTP Strict-Transport-Security (HSTS) Header | Fixation in Progress
CMS - Branch Collection Portal - RAAST and RTGS DMS | High | Weak Password Policy | Fixed
CMS - Branch Collection Portal - RAAST and RTGS DMS | High | Lack of TLS and Use of Non-FQDN in Production | Fixed
CMS - Branch Collection Portal - RAAST and RTGS DMS | High | DBG Team Access to Production with Security Configuration Privileges | Fixed
CRPL - Port Community System (PCS) APIs | High | Improper JWT Token Invalidation/Session Management Issue | Fixed
CRPL - Port Community System (PCS) APIs | High | Missing Rate Limiting | Fixed
CRPL - Port Community System (PCS) APIs | High | Host Header Injection | Fixed
CRPL - Port Community System (PCS) APIs | High | Domain Name Mismatch | Fixed
CRPL - Port Community System (PCS) APIs | Medium | Clear Text Transmission of Credentials | Fixation in Progress
CRPL - Port Community System (PCS) APIs | Medium | Password Complexity Vulnerability | Fixed
CRPL - Port Community System (PCS) APIs | Medium | Missing Security Headers | Fixed
CRPL - Port Community System (PCS) APIs | Medium | Fully Qualified Domain Name(FQDN) | Fixed
CRPL - Port Community System (PCS) APIs | Medium | Server Type Disclosure | Fixed
CRPL Bulk Govt Salary Converter | High | Privilege Escalation | Fixed
CRPL Bulk Govt Salary Converter | High | Arbitrary File Upload | Fixation in Progress
CRPL Bulk Govt Salary Converter | High | Session Token in GET Request | Fixed
CRPL Bulk Govt Salary Converter | High | Change Password Using GET METHOD | Fixed
CRPL Bulk Govt Salary Converter | High | UAT Environment is Publicly Accessible | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | Random generated Password not Complex | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | Insecure Connection Over HTTP | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | Internal Path Disclosure | Fixed
CRPL Bulk Govt Salary Converter | Medium | Missing Security Headers | Fixed
CRPL Bulk Govt Salary Converter | Medium | Swagger UI Disclosure | Fixed
CRPL Bulk Govt Salary Converter | Medium | Autocomplete Enabled on Sensitive Fields | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | Session Token Stored in Insecure Local Storage | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | SQL Queries and Verbose Messages Disclosed in Response | Fixed
CRPL Bulk Govt Salary Converter | Medium | Cross origin Resource sharing wild card Enabled | Fixed
CRPL Bulk Govt Salary Converter | Medium | Missing CSP Content Security Policy | Fixed
CRPL Bulk Govt Salary Converter | Medium | Server Version Disclosure | Fixation in Progress
CRPL Bulk Govt Salary Converter | Medium | Password History not Set | Fixed
CRPL PSW API | High | No Rate Limit upon each request | Fixation in Progress
CRPL PSW API | High | Previous Token Not Invalidate After Creating New | Fixation in Progress
CRPL PSW API | High | Brute Force Upon Authentication API | Fixation in Progress
CRPL PSW API | Medium | Missing Security Headers | Fixation in Progress
CRPL PSW API | Medium | Password Complexity | Fixation in Progress
CRPL PSW API | Medium | Server Information Disclosure | Fixation in Progress
CRPL PSW API | Medium | Logs Not Provided | Fixation in Progress
CRPL PSW API | Low | X-Powered-By | Fixation in Progress
CMS Branch Collection and backoffice portal | High | Reflected Cross-Site Scripting (XSS) | Fixation in Progress
CMS Branch Collection and backoffice portal | High | User Enumeration | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Improper Error Handling | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Password Not Change Upon First Login | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Session ID not removed after Logout | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Server Information Disclosure | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Unnecessary HTTP Methods Enabled | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Outdated JavaScript Library | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Missing HTTP Security Headers | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Content Security Policy Headers – Unsafe Directive | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Use of Outdated TLS Configuration | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | Autocomplete Enabled on Sensitive Fields | Fixation in Progress
CMS Branch Collection and backoffice portal | Medium | No maker checker control for user management/critical activities | Fixation in Progress