## Weekly Project Update
Sr. No. | Project / Issue | UAT/Live | Current NBP Remarks | PAYSYS Response | NBP Remarks / Action Required | Last Update Date
1 | IBFT & UBPS Workflow | UAT | Lastest Update? CR approved by NBP. |  |  | 2026-09-15
2 | SWAPS | UAT | SIT Complete. |  |  | 2026-09-15
3 | RAAST OTC Reversal | Live | No update – Pending since long |  |  | 2026-09-15
4 | Re Attempt | UAT | Email shared by NBP. Response Awaited from Paysys. |  |  | 2026-09-15
5 | Collection via Mobile app | UAT | Update required
6 | API Billers Data | UAT | Resonse awaited. |  |  | 2026-09-15
7 | OTC Biller – UOBS | UAT | UAT Complete |  |  | 2026-09-15
8 | OTC Biller – Pak Austria | UAT | UAT awaited |  |  | 2026-09-15
9 | OTC Biller – PHC | UAT | New Biller
10 | UBPS Issue | Live | Success response shared to channel but transactions failed at 1 Link end.
11 | RAAST Bulk Issue | Live | Unable to connect please try again. |  |  | 2026-10-05
12 | Advance Payment/ Control Gap | UAT | Slot for UAT if Required.

## Meeting Info
Meeting | Weekly Project Update (PAYSYS X NBP)
Meeting Date | 04-Sep-2026
Purpose | Track project status, PAYSYS response, NBP remarks/action items, and latest update date.