## Sheet1
Allocation | Category | Status | Mandate | Live Date | Update
Saad Asif | Collection | Under Scoping | GBMS | TBD | Under Development
Saad Asif | Collection | UAT | SWAPS | TBD | Scoping Done, SIT in process by Paysys.
Afzal | Collection | LIVE | NTC - National Telecommunication Centre | TBD | UAT Done, Circular pending
Mubashir | Payment | Under Scoping | HR Salary-Purpose IBT | TBD | Under scoping
Mubashir | Payment | UAT | Host to Host intergration for Payments | TBD | Initial meeting done with vendor and customer, SOW in process
Adnan Younis | R22 Upgrade | Under Scoping | R22 Upgrade | TBD | This matter is currently pending review by legal counsel.
Bhawan | Payment | Scoping | Govt Salaries & Pension (Putty) | TBD | Scoping.
Afzal | Collection | LIVE | BISEK | TBD | UAT Done, Circular pending
Afzal | Collection | LIVE | Mazhar School | TBD | UAT Done, Circular pending
Afzal | Collection | UAT | Pak Austria | TBD | API share with Paysys, Intial meeting done, connectivity in process
Afzal | Collection | LIVE | PASSPORT FEE MIS reporting and QR | TBD | SOW finalizated, FSD received, UAT Done. Production deployment and implenentaiton required, Under IS review, CMC approved.
Afzal | Collection | UAT | University of Balistan Skardu | TBD | API shared with Paysys, Development in process
Afzal | Collection | LIVE | University of SWAT | TBD | API shared with Paysys, UAT Done, circular pending
Afzal | Collection | LIVE | BISE BANNU | 2026-07-15 | API shared with Paysys, IPSEC form shared to paysys, Under UAT, Circular issued
Afzal | Admin | CMC | Admin MGMT | TBD | UAT Done.
Afzal | Collection | LIVE | E Stamping Sindh | TBD | Live.
Afzal | Collection | LIVE | Health Service Acadamy | 2026-07-15 | API shared with Paysys, UAT Done, Production connectivity done. Circular issued
Afzal | Collection | LIVE | Single Check Multiple Bills | TBD | Live.
Afzal | Collection | LIVE | LHC - Digitalization | 2026-07-17 | API shared with Paysys, Addition of Head of account in API, UAT done, production deployment and implementation required
Afzal | Collection | UAT | Encryption of Bulk Account upload - Is Issue | TBD | SOW and FSD approved. CRPL will provide the UAT patch.
Afzal | Collection | LIVE | SHC | 2026-06-03 | UAT DONE, Circular pending, Live
Afzal / Adnan | Collection | BAU | Branch collection/ API Billers | BAU | Business as usual.
Bhawan | PSW | LIVE | PSW AD Changes | 2026-08-07 | UAT DONE, IS REVIEW DONE, CMC Approved, Live
Bhawan | PSW | LIVE | PSW PCS | 2026-08-27 | UAT DONE, Under IS Review,Live.
Bhawan | Payment | LIVE | RAAST TTC | 2026-07-24 | Addition and update on RAAST TTC code, Live
Mubashir | Collection | Under Scoping | Collection of Dealer via App | TBD | BRD shared. Pending from Paysys and Mobile App team
Mubashir | Payment | LIVE | RAAST/RTGS DMS | 2026-04-13 | Live.
Mubashir | Payment | UAT | Raast OTC - Auto Reversal | TBD | Paysys has not developed Raast OTC auto reversal scenario while it was tested by Tayyab bhai.
Mubashir | Payment | Under Scoping | Raast QR Upload | TBD | Under Scoping.BRD Shared with crpl
Mubashir | Payment | CMC | Bulk SIDA Upload Limit 50 K | TBD | SOW finalized, FSD received, Under UAT,Under Is review. For CMC approval
Mubashir | Payment | LIVE | Resent of Title Fetch - SmartPAY | 2026-09-11 | SOW finalized, FSD received, Under UAT,Under Is review. For CMC approval
Mubashir | Payment | CMC | Status Update Payment | TBD | SOW finalized, FSD received, Under UAT
Mubashir | Payment | LIVE | Balance Inquiry Length Enhancement | 2026-05-19 | SOW finalized, FSD revised required. UAT done, Production deployment done
Mubashir | Payment | LIVE | RAAST OTC reason of rejection required | 2026-05-05 | SOW finalized, UAT Done. Production release received and deployed
Mubashir | Payment | LIVE | UBCS - Partail Payment | 2026-04-10 | UAT Done, DGB and OPS. CMC Approved,
Mubashir | Payment | BAU | Payment Portal Front-Office | BAU | Business as usual.
Mubashir | Collection | BAU | Raat OTC | BAU | Business as usual.
Saad Asif | Collection | CMC | Outward Clearing | TBD | DBG UAT Done,Under UAT at OPG and Core end
Saad Asif | Payment | IS Review | SIEM Intergration | TBD | Under UAT, Observation raised with CRPL, IS requested for logs.
Saad Asif | Collection | LIVE | CNIC Screening -ATA | 2026-02-06 | UAT DONE by DBG, Live.
Saad Asif | UBCS | LIVE | Discontinuation of SOAP to REST | 2026-06-08 | 1Link document shared, Paysys document received, SIT DONE, UAT DONE, CMC Approved
Saad Asif | Collection | LIVE | E-Stamping (Addition of property tax) | 2026-07-24 | API document received, meeting will be scheduled for kick off, Test Transaction performed and shared for validation, UAT DONE.
Saad Asif | Collection | LIVE | UBCS API Response | 2026-10-14 | Transactions with higher amounts will be processed first, while multithreading will enable faster transaction processing.
Saad Asif | UBCS | UAT | Control Gap - UBCS | TBD | Requirement shared with CRPL, SOW finalizaed, FSD finalized, currently under QA and will be moved to UAT upon approval.
Saad Asif | Payment | LIVE | RF Account on SmartPAY | 2026-05-19 | UAT Done. Shared with IT, UAT Done. Confirmation from Business team received. Deployment done,Live
Saad Asif | Payment | UAT | Payment File upload via Email /SFTP | TBD | BRD raised with CRPL, SOW finalized, FSD and efforts required, under development
Saad Asif | Payment | Under Scoping | IBFT & UBPS Workflow Change | TBD | FSD Approved
Saad Asif | Payment | LIVE | Tokinization on SmartPAY | 2026-06-08 | IS issue. UAT DONE for UBCS, RAAST, IBFT, CMC approved,Live
Saad Asif | Payment | BAU | Payment Portal-Back Office - Raast Bulk/SPHF | BAU | Business as usual.
Saad Asif | Collection | BAU | UBCS /Bulk | BAU | Business as usual.
Saad Asif | Payment | BAU | Cash over the counter (COC) | BAU | Business as usual.
Ayesha Khan | Collection | IS Review | Court Management System | TBD | Under Is review.
Ayesha Khan | payment | UAT | Virtual Account for supporting SIDA | TBD | Discussion going on between SOW DBG and CRPL.
Ayesha Khan | IS VAPT's Fixes | BAU | Remediating VAPT findings strengthens security. | BAU | Resolving the vulnerabilities identified during testing significantly improves our system's posture.
Ayesha Khan | Data Analytics | BAU | Data Analytics | BAU | Business as usual.
Adnan Younis | Payment | UAT | IBT Threading | TBD | Under UAT
Adnan Younis | Collection | UAT | PTCL Advance Payment | TBD | SOW and FSD approved. Currently under QA; will be moved to UAT after QA approval.
Adnan Younis | PSW | UAT | PSW Price Verification | TBD | Under UAT
Adnan Younis | Collection | Under Scoping | Banker Cheque collection via CRPL | TBD | CRPL is working on it and will share an update accordingly.
Adnan Younis | Payment | BAU | Vendor Payments | BAU | Business as usual.
Sania Malik | Payment | UAT | Enhancment of FT Amount limit for IBT | TBD | BRD Shared.
Sania Malik | Collection | Under Scoping | Punjab Health commission | TBD | API Shared
Sania Malik | Both | Under Scoping | ID locking for retired users | TBD | BRD Shared.
Zohaib Shahzad | Payment | Under Scoping | RAAST P2P | TBD | Meeting held between CRPL , PAYSYS and Smartpay Team.