## CRPL
CRF No | CRF Name | Stage | CRPL Remarks | NBP Remarks
734-26 | Host to Host | WIP | Under Efforts Estmation | SOW rasied to customer for review.
732-26 | B2G QR Upload Dated 4th Aug-26 | WIP | Under Efforts Estmation | SOW is Okay
733-26 | Server upgrade to 2022 | Closed | Efforts shared with CMO team. So Ali Noor will send CRF shortly | Mubashir is the POC
713-26 | Upload Account workflow - Encryption | TBD | Will share delivery time line as above three CRF's moved on UAT | UAT patch is awaited from CRPL.
730-26 | Automation of Encrypted Payment File Upload via Email in SMARTPAY Back Office Portal | UAT | UAT Patch Shared | Recived.
727-26 | Virtual Account for Supporting SIDA Transactions | TBD | SIT completed will share delivery time line this week | Response Awaited from CRPL
717-26 | IMPLEMENTATION OF SWAP | TBD | Development in process as per API doc. | Demo required from CRPL, TED shared with CRPL to intiate developmenet
710-26 | PSW MIS Phase III | WIP | Out of Eight, three reported already provide. Rest three more reporting we are providing till tomorrow | Six reports have been deployed to UAT. feedback on a few of them received by CRPL, some pertain to requirement understanding, while others have formatting issues that will be resolved.
747-25 | IBFT and UBPS workflow change | WIP | Need advice API from Paysys | SOW and API p[ending at Paysys end
728-26 | PTCL Advance Payment | WIP | QA in process and will try to send UAT patch at max by 22-Sep CO | Will Deliver this CRF at max by 18-Sep, UAT patch is awaited from CRPL.
723-26 | Control GAP | WIP | QA in process and will try to send UAT patch at max by 22-Sep CO | Will Deliver this CRF at max by 18-Sep, UAT patch is awaited from CRPL.
716-26 | PSW Centralized Digital Portal for Price Verification | UAT | UAT in process. In addition, pls look attachd email | Email raised to IT PMO by CRPL
708-26 | STATUS UPDATE FUNCTIONALITY | UAT | According to approved SOW/FSD, released deployed on UAT. Raast OTC we can not cater under this scope. | UNDER UAT, RAAST OTC to be incoprporate
714-26 | BRD for Title Fetch Re-Attempt Option | TBL | Production patch shared | LIVE
701-26 | Queue-Based - SIDA Bulk Upload & Bulk Payment | TBL | Please confirm UAT Completion | UNDER UAT, discussion required with qasim
749-25 | Govt Bulk Salary Customer Upload | UAT | UAT closure target require from OPG | No Update.
724-25 | Integration with SIEM | UAT | We cant confirm about R-22 Logs now | ISD issue is still OPEN on SIEM, meeting will be held between is and crpl
735-26 | Mobile App X SMARTPAY for Dealer Collection | WIP | WIP | Reuested objects provided by NBP team on 4th September
722-26 | OUTWARD Remittance Dated 4th May-26 | WIP | WIP | Waiting for detail BRD from OPG
733-26 | Server upgrade to 2022 | UAT | Internal approval received but NBP approval is still pendin | Will Revert
704-26 | Bill of Lading – PSW | TBL | Please confirm about Live status | LIVE
TBC | PICH2 | Hold | Waiting for CBS API | HOLD
TBC | Court Management | TBL | IS fixation patch shared in morning | White box required.
| UAT Issues | UAT | Will Revert back | Waiting to hear from CRPL
| 99 Timeout in IBFT title fetch NRSP | UAT | Prefix issue
| Resend Interface | LIVE | Observation shared with CRPL
| UBCS late Response Update | LIVE